CLINICAL TRIAL OPERATIONS

TRAINING WORKBOOK

An Operational Walkthrough of a Phase 3b Clinical Trial

Based on the INITIATE-PAH Protocol (CTP-PAH-001)

Prepared for: Clinical Trial Assistants, Clinical Trial Coordinators,

Clinical Trial Associates, Clinical Operations Associates and Site Management Associates

# 1. Executive Summary

This workbook was built as a training tool for people joining a clinical operations team, whether at a CRO or at a sponsor company. Rather than teaching Good Clinical Practice (GCP) as a list of abstract rules, it walks through a single, realistic Phase 3b trial from the moment a site is considered for the study through to database lock and archiving. The trial used throughout is INITIATE-PAH (protocol CTP-PAH-001), a mock protocol built for training purposes, comparing an initial triple oral therapy against an initial dual oral therapy in adults newly diagnosed with pulmonary arterial hypertension (PAH).

The intent is practical. A new Clinical Trial Assistant (CTA) or Clinical Trial Coordinator (CTC) rarely learns operations from the protocol text itself — protocols are written for regulators and investigators, not for the person who has to build the source documents, track IP accountability, or chase a missing signature on a delegation log. This workbook translates the protocol into the operational language that a coordinator, associate, or site management associate actually works in day to day.

Each chapter maps to a stage of the trial lifecycle: feasibility, start-up, patient journey, visit conduct, pharmacy and laboratory operations, vendor oversight, data management, monitoring, and close-out. Templates are included in the appendix so that trainees can see, in a concrete way, what a site readiness checklist, a delegation log, or a screening log actually looks like in practice.

A note on scope: this workbook does not interpret or predict clinical outcomes. INITIATE-PAH is a training protocol only, and no efficacy or safety conclusions should be drawn from it. The focus throughout is entirely operational — how the trial is run, not what it will show.

# 2. Study Synopsis

Before touching any operational plan, every new team member should be able to describe the study in plain language in under two minutes. If you cannot do that, you are not ready to build source documents, train site staff, or answer a monitor's question. The table below summarizes INITIATE-PAH the way it would typically be presented in a site initiation visit (SIV) slide deck, stripped of the regulatory phrasing found in the protocol itself.

| Element | Summary |
| --- | --- |
| Protocol | INITIATE-PAH, CTP-PAH-001, Version 2.0 (Amendment 1) |
| Phase | Phase 3b |
| Design | Multicenter, double-blind, randomized 1:1, placebo-controlled, parallel-group |
| Population | Adults 18–75 years, newly diagnosed (under 6 months), treatment-naïve WHO Group 1 PAH, confirmed by right heart catheterization (RHC) |
| Arms | Arm A: triple oral therapy (ERA-01 + PDE5i-01 + IPRA-01). Arm B: dual oral therapy (ERA-01 + PDE5i-01 + placebo) |
| Sample size | Approximately 240 participants, about 120 per arm |
| Sites / countries | Approximately 80–90 sites across roughly 20 countries |
| Primary endpoint | Change in pulmonary vascular resistance (PVR) from baseline to Week 26, measured by RHC |
| Core visit window | Screening (up to 28 days) through Week 26, plus a 30-day safety follow-up; optional extension visits every 6 months |
| Key oversight body | Independent Data Monitoring Committee (IDMC), with defined stopping rules |

What this means for site operations, in practical terms:

- Two invasive procedures anchor the whole trial (RHC at screening and again at Week 26) — these are the visits that must never slip.

- The comparator drug, IPRA-01, does not start until Day 15 and is titrated weekly through Week 12, which drives a heavy phone-contact burden on the coordinator.

- Randomization and both study-drug supply and unblinding all run through an Interactive Response Technology (IRT) system — nothing about drug dispensing happens without it.

- Because the population is treatment-naïve and newly diagnosed, recruitment depends heavily on referral relationships with pulmonology and cardiology clinics rather than on trial advertising.

# 3. Study Design Review

This chapter looks at the design elements of INITIATE-PAH that most directly shape day-to-day site work. A coordinator does not need to be a statistician, but does need to understand why the design looks the way it does, because that understanding drives how visits are scheduled, how deviations are triaged, and how much the study depends on a handful of critical procedures.

## 3.1 Why Triple vs. Dual Therapy

The comparison at the center of this study is between adding a third oral agent (IPRA-01, a prostacyclin receptor agonist analogue) to standard dual therapy versus keeping patients on dual therapy with a matched placebo. Operationally, this means the two background drugs (ERA-01 and PDE5i-01) are given open-label to everyone, and only the third drug is blinded. New staff sometimes assume the whole regimen is blinded — it is worth stating clearly in training that it is not, and that only IPRA-01 versus placebo is masked.

## 3.2 Randomization and Stratification

Randomization is 1:1 through IRT, stratified by region (North America versus rest of world) and by baseline WHO Functional Class (I/II versus III/IV). For the coordinator, the practical implication is that the eligibility confirmation and the WHO FC assessment must be locked in before the randomization call is made in IRT — an incorrect or late FC entry can misstratify a patient and become a reportable protocol deviation.

## 3.3 Blinding Structure

Participants, investigators, and outcome assessors are blinded to IPRA-01 versus placebo. Emergency unblinding is available through IRT for safety reasons. Sites should know, before the first patient is even screened, who at the site is authorized to request unblinding and what the escalation path is, because in an emergency this is not the moment to be looking up a phone number.

## 3.4 Primary and Secondary Endpoints — Operational Reading

The primary endpoint, change in PVR from baseline to Week 26, depends entirely on a well-executed RHC performed to a standardized technique (correct catheter position, zeroing, and measurement at end-expiration). Key secondary endpoints — 6-minute walk distance (6MWD), Borg Dyspnea Index, WHO Functional Class, and NT-proBNP — depend on trained, consistent raters using the same equipment and, where possible, the same time of day for each assessment. None of this is exotic, but it is exactly the kind of detail that separates a clean dataset from one full of queries.

## 3.5 Study Duration and Extension

The core observation period runs to Week 26, with an end-of-study (EOS) visit roughly 30 days after the last dose or early discontinuation. Participants may continue into an optional long-term extension with visits every six months, up to 24 months. Coordinators should track which patients are extension-eligible separately, since supply forecasting and monitoring visit planning both change once a site moves into the extension phase.

# 4. Site Feasibility Assessment

Feasibility is where operational risk is either caught early or quietly built into the study for the next two years. A feasibility questionnaire that is filled out optimistically, without an honest look at referral volume or catheterization lab access, tends to surface as a low-enrolling site six months later — a much more expensive problem to fix.

## 4.1 Questions a Feasibility Assessment Must Answer

- Does the site have realistic access to newly diagnosed, treatment-naïve PAH patients — typically through a pulmonary hypertension referral network — given the six-month diagnosis window in the protocol?

- Is right heart catheterization available on-site, or would patients need to be referred elsewhere for both the screening and Week 26 procedures? A referral pathway that adds scheduling delay is a direct threat to the Week 26 visit window.

- Does the site have a locked, temperature-monitored pharmacy storage area suitable for IP, and staff available to manage receipt, dispensing, and reconciliation?

- Can the site commit staff time to weekly phone contacts during the Day 15 to Week 12 IPRA-01 titration period, on top of routine clinic workload?

- Is there central laboratory shipping infrastructure in place (courier pick-up, appropriate storage for aliquots) given the monthly liver and hemoglobin testing requirement?

- Has the site run a comparably complex double-blind, multi-drug protocol before, and can current staff describe IRT-based drug assignment without prompting?

## 4.2 Realistic Site Profile

For a trial like INITIATE-PAH, the strongest sites are typically pulmonary hypertension centers of excellence or academic cardiology/pulmonology programs with an existing RHC service and a track record in PAH trials. A general cardiology practice without in-house catheterization, or without a steady referral stream of newly diagnosed (not previously treated) patients, is a weaker candidate regardless of how enthusiastic the investigator is at the feasibility call.

## 4.3 Common Feasibility Mistakes

- Overestimating the eligible population by counting all PAH patients seen at the site, rather than only those who are newly diagnosed and treatment-naïve.

- Assuming an affiliated hospital's cath lab slots are automatically available on the tight windows the protocol requires.

- Underestimating coordinator time needed for the weekly titration calls, which run for roughly ten weeks per patient.

- Not confirming pharmacy capacity for a three-drug regimen with a blinded and an open-label component before commitment.

# 5. Study Start-Up Activities

Start-up is the phase where a site moves from 'selected' to 'ready to enroll.' It is also where most avoidable delays happen, because a lot of start-up work runs in parallel across different people and organizations, and a hold-up in one thread (say, contract signature) can block everything downstream even if the ethics submission is finished early. The sub-sections below follow the main workstreams a CTA or CTC will touch during start-up on a study like INITIATE-PAH.

## 5.1 Ethics Submission

The site (or a central IRB, depending on the country and sponsor model) must approve the protocol, the Investigator's Brochure, and the informed consent form (ICF) in the local language before any study-specific procedure occurs — including the screening RHC. For INITIATE-PAH, the ICF needs to reflect the invasive nature of RHC, the blinded component of treatment, the WOCBP contraception and monthly pregnancy testing requirements, and the defined liver-enzyme monitoring pathway. A coordinator should track ethics approval as a hard gate: no consent can be obtained, and therefore no pre-Day-1 RHC used for eligibility, until approval is in hand.

## 5.2 Contracts and Budget

The clinical trial agreement and the site budget are negotiated in parallel with, but independent of, ethics review. Because INITIATE-PAH involves an invasive procedure (RHC) performed twice per patient, plus monthly central lab draws and weekly coordinator phone contacts through Week 12, the budget needs to reflect a genuinely higher-complexity fee structure than a simple oral-only trial. Chapter 10 covers this in more detail; the point to flag here is that budget finalization is frequently the true rate-limiting step in start-up, even when everyone remembers to blame ethics.

## 5.3 Vendor Onboarding

Before first patient in, the site needs active accounts and, where applicable, completed training with: the central laboratory (for kit shipment and monthly draws), the IRT/IWRS vendor (for randomization, kit assignment, and emergency unblinding), courier services for ambient lab shipments, and — where used — a home health or phlebotomy vendor for participants who cannot easily travel for the monthly labs. Each of these needs its own account provisioning and, in most cases, a signed confidentiality or data processing agreement.

## 5.4 System Access

A realistic access list for INITIATE-PAH includes: the EDC (electronic data capture) system, IRT/IWRS, the central lab portal, the pharmacovigilance (PV) safety portal for SAE reporting, an e-portal or e-mail channel for ethics submissions, a CTMS if the sponsor uses one, ePRO if patient-reported outcomes are collected electronically, and a training LMS for vendor-specific modules. New coordinators are often surprised by how many separate logins this adds up to — building an access tracker at start-up (who has access to what, and when it was granted) avoids scrambling later.

## 5.5 Staff Training

Protocol-specific training should cover, at minimum: the RHC procedure and documentation requirements, 6MWT administration to a standardized method, WHO Functional Class assessment, the liver-enzyme follow-up algorithm, IP dispensing and accountability, and the consent process for a study with an invasive baseline procedure. Training completion should be documented and filed — this becomes part of the Investigator Site File (ISF) and is one of the first things a monitor checks at the first monitoring visit.

## 5.6 Site Initiation Visit (SIV)

The SIV is the last gate before enrollment opens. A well-run SIV for this protocol walks through the full visit schedule, the RHC standardization requirements, IP storage and dispensing logs, the IRT randomization and titration workflow, the liver safety algorithm, and pregnancy testing and contraception documentation for WOCBP. By the end of the SIV, every role at the site should know exactly what they are responsible for at Day 1 — this is best confirmed with a signed delegation log (see Appendix).

# 6. Patient Journey

Mapping the patient journey end-to-end helps a new coordinator see how clinical assessments, IP logistics, and data entry all have to land on the same day without colliding. The workflow below reflects the INITIATE-PAH visit structure.

## 6.1 Journey Workflow

- Pre-screening / Referral — Patient identified through a PAH referral network as newly diagnosed (under 6 months) and treatment-naïve; initial eligibility discussion with the referring physician.

- Consent — ICF reviewed and signed in the participant's own language before any study-specific procedure; site staff authorized on the delegation log conduct the consent discussion.

- Screening (Day −28 to Day −1) — Eligibility confirmed; baseline RHC performed (a pre-consent RHC done at the site within 28 days of Day 1 may be used if consent is obtained before enrollment); demographics, medical history, physical exam, vitals, WHO FC, 6MWD/Borg, central labs, and serum pregnancy test (WOCBP) collected.

- Day 1 (Randomization) — Final eligibility confirmed; participant randomized 1:1 via IRT, stratified by region and WHO FC; ERA-01 and PDE5i-01 (open-label) dispensed; urine pregnancy test for WOCBP.

- Day 8 — Interim safety and tolerability check (visit or phone call, per protocol windows).

- Day 15 — Blinded IPRA-01 or placebo initiated; up-titration schedule begins.

- Weekly Phone Calls (through Week 12) — Coordinator contacts participant to review tolerability, guide up-titration per the dosing table, and capture any adverse events.

- Week 12 Visit — Vitals, WHO FC, 6MWD/Borg, labs, biomarkers (NT-proBNP), IP dispensing and return, and reconciliation of the titration period.

- Week 26 Visit (Primary Endpoint) — Second RHC; full efficacy and safety assessment battery; this is the visit the entire trial is powered around, and it should never be scheduled outside its ±14-day window without a strong operational reason.

- End of Treatment (EOT) / Early Discontinuation (if applicable) — Triggered by withdrawal, pregnancy, unacceptable toxicity, protocol-defined liver thresholds, or other early-discontinuation criteria; EOT/EOS safety visit performed regardless of the reason for stopping.

- End of Study (EOS) — Approximately 30 days after the last IP dose or early termination; final safety assessment and, for WOCBP, a final pregnancy test.

- Optional Extension — Visits every 6 months up to Month 24 for participants continuing into the long-term extension.

A few operational notes worth flagging to new staff: the weekly phone-call block between Day 15 and Week 12 is the single heaviest coordinator workload period per patient, and it is easy to underestimate when planning caseload. The Week 26 RHC is the visit most likely to need advance scheduling with an external cath lab if the site does not have in-house capability — this should be pencilled in at the Week 12 visit, not the week before Week 26.

# 7. Visit Assessment Matrix

This matrix is the kind of reference a coordinator keeps open on a second monitor during a patient visit. It summarizes purpose, assessments, laboratory activity, IP actions, source documentation, and the staff role typically responsible, visit by visit, based on the INITIATE-PAH Schedule of Assessments.

| Visit | Purpose | Assessments | Laboratory | IP Activity | Source Documents | Responsible Staff |
| --- | --- | --- | --- | --- | --- | --- |
| Screening (Day −28 to −1) | Confirm eligibility | Med. history, physical exam, vitals, WHO FC, 6MWD/Borg, RHC | Central labs, serum pregnancy (WOCBP) | None | Eligibility checklist, RHC report, ICF | PI/Sub-I, Research Nurse |
| Day 1 (Randomization) | Enroll and randomize | Vitals, physical exam | Urine pregnancy (WOCBP) | Randomize via IRT; dispense ERA-01, PDE5i-01 | IRT confirmation, dispensing log | PI/Sub-I, Coordinator, Pharmacist |
| Day 8 | Early safety check | AE review, concomitant meds | None routine | Compliance check | Visit/phone note | Coordinator |
| Day 15 | Start blinded IP | AE review, tolerability | None routine | Dispense IPRA-01/placebo; begin titration | Dispensing log, titration record | Coordinator, Pharmacist |
| Weekly Calls (to Week 12) | Guide titration, monitor AEs | Tolerability review | None routine | Titration step confirmed via IRT | Phone call log | Coordinator |
| Week 12 | Interim efficacy/safety | Vitals, WHO FC, 6MWD/Borg, biomarkers | Central labs, liver/hemoglobin, pregnancy | IP dispensing and return | eCRF source, lab requisitions | Coordinator, Rater, Pharmacist |
| Week 26 (Primary Endpoint) | Primary endpoint assessment | Vitals, WHO FC, 6MWD/Borg, RHC (2nd) | Central labs, liver/hemoglobin, pregnancy, biomarkers | IP dispensing and return | RHC report, eCRF source | PI/Sub-I, Coordinator, Rater |
| EOT / EOS | Close treatment or exit safely | Vitals, physical exam, AE review | Final labs, pregnancy (if WOCBP) | Final IP return and reconciliation | EOT/EOS form, reconciliation log | PI/Sub-I, Coordinator, Pharmacist |
| Extension (every 6 mo.) | Long-term follow-up | Vitals, WHO FC, AE review | Per extension schedule | Ongoing dispensing | eCRF source | Coordinator, PI/Sub-I |

Note: laboratory testing for liver aminotransferases, bilirubin, and hemoglobin is required monthly throughout the study regardless of visit type, and can occur at the site, a satellite laboratory, or through home phlebotomy — this monthly cadence runs independently of the visit schedule above and needs its own tracking mechanism.

# 8. Roles and Responsibilities

A RACI matrix (Responsible, Accountable, Consulted, Informed) is a useful way to make sure two people don't assume the other is handling something critical — IP accountability and SAE reporting are the two areas where this gap causes the most damage. The matrix below reflects a typical site team structure for a study of this complexity.

| Activity | PI / Sub-I | Coordinator | Pharmacist | Lab Tech | Data Manager/Monitor |
| --- | --- | --- | --- | --- | --- |
| Eligibility confirmation | A/R | C | I | I | I |
| Informed consent | A | R | I | I | I |
| RHC performance and interpretation | R/A | C | I | I | I |
| 6MWT / WHO FC assessment | C | R | I | I | I |
| Randomization (IRT) | A | R | C | I | I |
| IP receipt, storage, dispensing | A | C | R | I | I |
| IP accountability/reconciliation | A | C | R | I | C |
| Sample collection and processing | C | C | I | R | I |
| Sample shipment / chain of custody | I | C | I | R/A | I |
| AE/SAE identification | A/R | R | C | I | I |
| SAE reporting to PV (within 24h) | A | R | I | I | I |
| Liver safety follow-up decisions | A/R | C | I | I | I |
| eCRF data entry | I | R | I | I | A |
| Query resolution | C | R | I | I | A |
| Protocol deviation documentation | A | R | I | I | C |
| Monitoring visit hosting | C | R/A | C | C | I |

A pattern worth pointing out to trainees: the coordinator is 'Responsible' for far more line items than any other role. This is realistic — the coordinator is the operational hub of the site — but it is also exactly why delegation logs, backup coverage plans, and clear escalation paths to the PI matter so much on a protocol with this many moving parts.

# 9. Pharmacy Operations

Pharmacy operations on INITIATE-PAH are more involved than on a simple single-drug oral trial because the site is managing three products with two different assignment logics: ERA-01 and PDE5i-01 are open-label and dispensed by standard prescribing logic, while IPRA-01/placebo is IRT-assigned, blinded, and titrated on an individualized weekly schedule from Day 15 through Week 12.

## 9.1 Storage

IP is stored in a locked, temperature-monitored area with access limited to authorized pharmacy staff. A separate, clearly labeled area is maintained for returns and quarantined stock (for example, product implicated in a temperature excursion) so that it cannot be accidentally re-dispensed.

## 9.2 Dispensing Logic

- ERA-01 and PDE5i-01: dispensed per standard site prescribing practice, open-label, starting Day 1 (PDE5i-01 begins at 20 mg daily for 7 days, then steps to 40 mg daily as tolerated).

- IPRA-01/placebo: kit assignment comes from IRT, not from pharmacy judgment. The titration table in the protocol (200 mcg BID at Day 15, increasing in 200 mcg BID increments roughly weekly to a maximum of 1600 mcg BID by Week 12, held stable through Week 26) must be followed exactly as confirmed through IRT at each step, with temporary down-titration permitted for tolerability.

## 9.3 Accountability and Reconciliation

Every receipt, dispense, return, and destruction event is logged. At each monitoring visit, accountability is reconciled against the eCRF and IRT records — a mismatch here (for example, a dispensed kit number that does not match the IRT-assigned kit number) is one of the most common and most serious findings in this type of trial, because it can call blinding integrity into question.

## 9.4 Dose Adjustments for Tolerability

Hypotension, headache, and gastrointestinal adverse events are managed with a step-down titration or a temporary hold, resuming per protocol once resolved. The pharmacist and coordinator need a shared, real-time way to track where each patient currently sits on the titration table — a spreadsheet is fine early in a trial, but for a site running more than a handful of patients this quickly becomes the kind of thing best tracked inside IRT or a dedicated tracker to avoid dosing errors.

# 10. Laboratory Operations

INITIATE-PAH relies on a central laboratory for the core safety and biomarker panel, with monthly liver and hemoglobin testing running continuously through the study regardless of visit schedule. This monthly cadence is easy to lose track of if it is not tracked separately from the main visit calendar.

## 10.1 What the Central Lab Covers

- General safety chemistry and hematology, drawn at protocol-specified visits.

- Monthly liver aminotransferases (ALT/AST), total and direct bilirubin, and hemoglobin — mandatory throughout the study, and can be drawn at the site, a satellite lab, or via home phlebotomy for patients who cannot easily travel.

- NT-proBNP biomarker sampling at defined timepoints.

- Coagulation testing as part of the general safety panel.

## 10.2 Liver Safety Follow-Up — Operational Sequence

This is one of the most operationally important algorithms in the protocol, and every coordinator on this study should be able to walk through it without looking it up:

- If ALT or AST is confirmed above 3× the upper limit of normal (ULN), repeat testing within 48–72 hours and add bilirubin and ALP; assess the patient for symptoms.

- If ALT or AST exceeds 5× ULN, or ALT/AST exceeds 3× ULN together with bilirubin above 2× ULN without evidence of cholestasis, study drugs are held, monitoring frequency is increased, a Hy's Law evaluation is considered, and the event is reported as an SAE if criteria are met.

- Dosing resumes once values improve to below 3× ULN and the patient is asymptomatic.

Because this sequence has hard deadlines (48–72 hours for repeat testing) and directly affects IP dosing, it should be built into site training as a standalone module, not folded quietly into general safety training.

## 10.3 Sample Handling and Shipment

Site facilities need a centrifuge, appropriate ambient/4°C temporary storage, and a −20°C freezer for aliquots, along with shipping supplies and a reliable courier relationship for ambient lab shipments. Chain-of-custody documentation should travel with every shipment, and any temperature excursion in storage or transit needs to be logged and reported to the central lab and sponsor promptly, since it can affect sample validity.

## 10.4 Local vs. Central Testing at Screening

The protocol allows local laboratory testing at screening as an alternative to central lab turnaround time, provided the central lab kit is drawn in parallel and all local results (with local normal ranges) are entered in the eCRF. This is a useful option for confirming eligibility quickly, but the parallel central draw cannot be skipped.

# 11. Vendor Management

A trial of this complexity runs on a network of vendors, and the site-facing operations team needs a working relationship with each one, even though most vendor contracts sit at the sponsor or CRO level rather than the site level.

| Vendor | Role in the Study | Site-Level Touchpoint |
| --- | --- | --- |
| Central Laboratory | Kit supply, sample analysis, results reporting | Kit ordering, requisitions, shipment scheduling |
| IRT / IWRS | Randomization, kit assignment, titration tracking, emergency unblinding | Daily use for enrollment, dispensing, and titration confirmation |
| Courier (ambient) | Transport of lab shipments to central lab | Pick-up scheduling, shipment tracking |
| Home Health / Phlebotomy | Optional draws for participants unable to travel monthly | Coordinator schedules visits, confirms results are received |
| EDC Provider | Electronic case report form platform | Data entry, query resolution, audit trail |
| Pharmacovigilance (PV) Vendor/Portal | SAE intake and processing | 24-hour SAE submission |

The practical skill here is knowing which vendor to call for which problem — a missing lab kit is a central lab issue, a randomization error is an IRT issue, and a late SAE acknowledgment is a PV portal issue. New coordinators often route everything through the monitor by default; building direct vendor contact familiarity during start-up saves time once the site is enrolling.

# 12. Data Management

Good data management is less about typing fast into the EDC and more about a disciplined chain from what actually happened with the patient to what is recorded in the system. This chapter walks through that chain.

## 12.1 Source Documentation

Source is the first place a piece of data is recorded — a nursing note, an RHC printout, a lab report, a signed ICF. It must be contemporaneous, attributable, legible, original (or a certified copy), accurate, and complete — the ALCOA+ principle. For INITIATE-PAH, source includes RHC reports, 6MWT worksheets, WHO FC assessment notes, IP dispensing logs, and the weekly titration phone call notes.

## 12.2 eCRF and EDC

The eCRF is the study-specific case report form built inside the EDC platform. Data entered into the eCRF must be transcribed from source, not invented at the point of entry. The EDC applies real-time edit checks, keeps a full audit trail of every change, and manages the query workflow between site and monitor/data manager.

## 12.3 Queries

A query is raised when data looks incomplete, inconsistent, or out of range — for example, a Week 26 visit date that falls outside the ±14-day window, or a WHO FC value that does not match what is documented in source. The coordinator's job is to resolve the query against source, not just to make the system accept a value. Query aging (how long a query sits open) is one of the metrics monitors and data managers watch closely.

## 12.4 Monitoring — Data Role

Monitors perform source data verification (SDV) and, on many current studies, risk-based monitoring (RBM) that focuses attention on critical data and processes — eligibility, IP exposure, primary and secondary endpoint data, safety reporting, pregnancy testing, and visit-window adherence. Monitoring visits are also where accountability logs, delegation logs, and training records are checked against what the eCRF and IRT show.

## 12.5 Database Lock

Database lock happens once all data is entered, all queries are closed, SDV/RBM activities are complete, and the data has been reviewed and signed off by the relevant parties (data management, biostatistics, medical monitor). After lock, no further changes are made to the dataset without a formal, documented unlock process. For a site, this means the real deadline is not the Week 26 visit — it is having every open query on every patient resolved well before the sponsor's planned lock date.

# 13. Risk Register

A risk register is a living document, reviewed regularly at site and study level, not a one-time exercise done at start-up and then filed away. The entries below are realistic examples for a study like INITIATE-PAH, not an exhaustive list.

| Risk | Impact | Likelihood | Severity | Mitigation |
| --- | --- | --- | --- | --- |
| Week 26 RHC scheduling delay (external cath lab dependency) | Primary endpoint visit outside window | Medium | High | Pre-book cath lab slot at Week 12 visit; maintain backup facility agreement |
| Missed weekly titration call | Incorrect/delayed dose step; potential deviation | Medium | Medium | Shared titration tracker; backup coordinator coverage plan |
| Liver enzyme threshold missed or follow-up testing delayed beyond 48–72h | Safety risk; potential SAE under-reporting | Low | High | Lab result alert routing to coordinator and PI same day; documented escalation path |
| IP dispensing/kit number mismatch with IRT | Blinding integrity concern; accountability finding | Low | High | Dual verification of kit number at every dispense; pharmacist sign-off |
| WOCBP monthly pregnancy test missed | Protocol non-compliance; potential safety exposure | Medium | High | Calendar reminders tied to eCRF; coordinator monthly tracking log |
| Screen failure due to late referral (outside 6-month diagnosis window) | Recruitment delay | Medium | Medium | Strengthen referral pathway; educate referring physicians on window |
| Central lab shipment temperature excursion | Sample invalidity, repeat draw needed | Low | Medium | Courier SLA review; temperature logger on all shipments |
| Delegation log not updated for new staff | GCP/audit finding | Medium | Medium | Delegation log review at every monitoring visit |
| SAE reported outside 24-hour window | Regulatory compliance breach | Low | High | SAE reporting refresher training; visible reporting deadline poster/reminder |

# 14. Monitoring Activities

Monitoring on INITIATE-PAH follows a risk-based approach, meaning not every data point gets 100% source data verification — attention is concentrated on the areas that matter most to patient safety and to the integrity of the primary endpoint.

## 14.1 High-Risk Areas Requiring Monitoring Attention

- Eligibility criteria at screening, particularly the RHC-confirmed hemodynamic thresholds and the negative acute vasoreactivity requirement for applicable etiologies.

- IP exposure and accountability, especially the IPRA-01/placebo titration record against IRT.

- Primary and key secondary endpoint data — RHC measurements, 6MWD, WHO FC — for consistency with source and standardized methodology.

- Safety reporting timelines, especially SAE submission within 24 hours and liver enzyme follow-up within the 48–72 hour window.

- WOCBP pregnancy testing and contraception documentation.

- Visit window adherence, particularly for Week 26.

## 14.2 What a Monitoring Visit Typically Covers

- Review of the Investigator Site File for completeness — training records, delegation log, ethics correspondence, essential documents.

- Source data verification against eCRF entries for critical data points.

- IP accountability reconciliation against pharmacy logs and IRT.

- Review of open queries and outstanding action items from prior visits.

- Confirmation of informed consent process for any newly enrolled participants.

- A closing discussion with the PI or delegate covering findings, action items, and target resolution dates.

## 14.3 The Study Critical Data Concept

Not all data carries equal weight. 'Critical data' on this protocol centers on eligibility confirmation, RHC results, IP exposure, the primary and key secondary endpoints, and safety reporting. Framing monitoring priorities this way helps a coordinator understand why a monitor might spend an hour on the RHC source documentation and five minutes on a routine vitals entry — it is not arbitrary; it reflects where an error would actually matter to the study.

# 15. Study Close-Out

Close-out is not a single visit; it is a sequence of activities that, done properly, leaves the site's records defensible for years after the last patient has left the study.

## 15.1 Site-Level Close-Out Activities

- Confirm all participants have completed EOT/EOS or are appropriately accounted for (withdrawal, death, lost to follow-up, ongoing extension).

- Final IP reconciliation and return/destruction per pharmacy SOPs, with documentation retained.

- Resolution of all outstanding queries and monitoring action items.

- Final source data verification and close-out monitoring visit.

- Confirmation that the Investigator Site File is complete per the ICH E6 Essential Documents list, including training records, delegation logs, and correspondence.

- Return or secure destruction of any remaining study materials per the sponsor's instructions.

## 15.2 Record Retention

Records are retained by the investigator for as long as required by the sponsor's clinical study agreement and applicable national or international regulations, whichever period is longest. If a site cannot guarantee on-site archiving for the full retention period, arrangements are made with the sponsor for secure off-site storage that respects data confidentiality and allows retrieval in the event of a regulatory inspection. No study document is destroyed without prior written sponsor approval.

## 15.3 Database Lock Alignment

Site-level close-out and database lock are related but distinct milestones. A site can be operationally 'closed' (no more visits, IP reconciled) while its data is still contributing to open queries elsewhere in the study. The coordinator's real target is having every query on every one of their patients closed well ahead of the sponsor's planned lock date, not just finishing the last patient visit.

# 16. Lessons Learned

This chapter collects the kind of practical insight a coordinator typically only picks up after living inside a protocol like this for a few months. Reading it in advance will not replace that experience, but it should shorten the learning curve.

- The titration phase (Day 15 to Week 12) is the real workload driver on this study, not the visit schedule on paper. Caseload planning should weight patients by how many are currently in active titration, not just by total enrolled count.

- Treat the Week 26 RHC as the visit the whole trial depends on. If your site relies on an external cath lab, build the booking conversation into the Week 12 visit checklist so it never becomes a last-minute scramble.

- The liver safety algorithm has hard timeframes (48–72 hours) built into it. Do not let it live only in the protocol PDF — put the thresholds and required actions somewhere the coordinator sees them without searching.

- Only IPRA-01 versus placebo is blinded; the other two drugs are open-label. This distinction affects how you talk to patients about their treatment and what a monitor will and will not ask about regarding blinding integrity.

- Monthly liver and hemoglobin testing runs independently of the visit calendar. It needs its own tracking line, or it will quietly slip, especially for patients using home phlebotomy.

- WOCBP contraception and pregnancy testing documentation is one of the more common audit findings on trials with a long treatment period — build it into the same monthly tracking mechanism as the liver labs.

- A dispensed kit number that does not match the IRT-assigned number is a serious finding, not a paperwork nuisance — it goes to the heart of blinding integrity and IP accountability.

- Protocol amendments matter operationally even when they read as small in the summary. Amendment 1 to this protocol widened the Week 26 visit window and added a biomarker timepoint — both details that affect scheduling and should trigger a specific staff briefing, not just a note in the ISF.

- Delegation logs and training records are usually the first thing checked at a monitoring visit. Keeping them current in real time is far less work than reconstructing them retrospectively.

# Appendix — Operational Templates

The templates in this appendix are simplified working examples, intended to show trainees the structure and level of detail expected in real site documents. Sites should adapt these to their own SOPs and to sponsor-provided versions where applicable.

## A. Site Readiness Checklist

| Item | Status (Y/N) | Comments |
| --- | --- | --- |
| Ethics/IRB approval obtained for protocol, IB, and ICF |  |  |
| Clinical trial agreement and budget fully executed |  |  |
| Pharmacy storage area assessed and compliant (locked, temperature-monitored) |  |  |
| IRT/IWRS access provisioned and training completed |  |  |
| EDC access provisioned and training completed |  |  |
| Central lab account active; kit supply confirmed |  |  |
| Courier/shipment process confirmed |  |  |
| RHC capability confirmed (on-site or referral pathway with scheduling agreement) |  |  |
| 6MWT corridor and equipment (stopwatch, pulse oximeter, BP device) available |  |  |
| Delegation log completed and signed by PI |  |  |
| Protocol-specific staff training completed and documented |  |  |
| SIV completed |  |  |

## B. Delegation of Authority Log

| Staff Name | Role | Delegated Task(s) | Signature | Dates Active (From–To) |
| --- | --- | --- | --- | --- |
|  | Principal Investigator | Overall responsibility; eligibility sign-off; safety decisions |  |  |
|  | Sub-Investigator | Eligibility assessment; consent; medical decisions |  |  |
|  | Study Coordinator | Consent facilitation; visit scheduling; data entry; IP accountability support |  |  |
|  | Pharmacist/Designee | IP storage, dispensing, accountability |  |  |
|  | Rater | 6MWT and WHO FC assessments |  |  |
|  | Lab Technician | Sample processing and shipment |  |  |

## C. Visit Checklist (Example — Week 26 Visit)

| Task | Completed (Y/N) | Notes |
| --- | --- | --- |
| Confirm visit falls within ±14-day window |  |  |
| Vitals, physical exam, weight recorded |  |  |
| WHO Functional Class assessed |  |  |
| 6MWT and Borg Dyspnea Index performed per standardized method |  |  |
| RHC performed and report filed in source |  |  |
| Central labs drawn (chemistry, hematology, liver/hemoglobin, biomarkers) |  |  |
| Pregnancy test performed (WOCBP) |  |  |
| IP dispensed and/or returned; accountability updated |  |  |
| AE/concomitant medication review completed |  |  |
| eCRF entries completed from source |  |  |

## D. Risk Register Template

| Risk | Impact | Likelihood | Severity | Mitigation / Owner |
| --- | --- | --- | --- | --- |

## E. Screening Log

| Subject # | Screening Date | Consent Date | Eligible (Y/N) | Screen Fail Reason (if applicable) | Randomization Date (if enrolled) |
| --- | --- | --- | --- | --- | --- |

## F. Enrollment Log

| Subject # | Randomization Date | Treatment Arm (per IRT) | Site ID | WHO FC at Baseline | Status (Active/EOT/EOS/Withdrawn) |
| --- | --- | --- | --- | --- | --- |

## G. Monitoring Visit Action Log

| Visit Date | Finding Category | Description / Action Required | Owner | Target Resolution Date |
| --- | --- | --- | --- | --- |